## Slide 1
30th April. Re-implement
Package by Gould[2].
14th June. Finish Convex Optimization Reading
Research Session
Start
Catching Up Session Start
1st Feb.
5th July. Finish Pseudo-Boolean Survey
25th July. Finish related work searching & studying.
15th Sep. Draft of project report.
10th Oct. Finish project report.
15th Oct. Finish presentation preparation
Project End

## Slide 2
Date | Goal | Outcome
1-Feb | Project start | 
30-Apr | Re-implement Package by Gould[2]. | An exctutable software
14-Jun | Finish Convex Optimization Reading | A report on methods of proving convexity
5-Jul | Finish Pseudo-Boolean Survey | A report on graph-cuts related methods
25-Jul | Finish related work searching & studying. | A repository of related papers and a to-do list regards those papers
15-Sep | Draft of project report. | Finish the skeleton of project paper
10-Oct | Finish project report. | A qualified paper
15-Oct | Finish presentation preparation | A PowerPoint file