## Sheet1
Date | Goal | Outcome
2016-02-01 | Project start
2016-04-30 | Re-implement Package by Gould[2]. | An exctutable software
2016-06-14 | Finish Convex Optimization Reading | A report on methods of proving convexity
2016-07-05 | Finish Pseudo-Boolean Survey | A report on graph-cuts related methods
2016-07-25 | Finish related work searching & studying. | A repository of related papers and a todo list regards those papers
2016-09-15 | Draft of project report. | Finish the skeleton of project paper
2016-10-10 | Finish project report. | A qualified paper
2016-10-15 | Finish presentation preparation | A powerpoint file